## Milestone
MVP | Product | Product Description | Start date | End date | Remarks
1 | Type Details | Alert Regarding type of issues with Count | 2019-08-09 | 2019-08-10
2 | Severity Details | Alert Regarding severity of issues with Count | 2019-08-12 | 2019-08-13
Final | Report | Complete report of Onboarded applications with type of issues and severity. | 2019-08-13 | 2019-08-14

## MVP1
Product | Description | Working Hours | Responsibility
UI | PopUp Report Regarding Type of Issues | 5 | Aman Vijay
Service | Filtering Issue Type Details From Api (Service Implementation) | 5 | Amit Kumar
Deployment | N/A

## MVP2
Product | Description | Working Hours | Responsibility
UI | PopUp Report Regarding Severity Count of Issues | 5 | Sakshi Goyal
Service | Filtering Severity Details From Api(Functional Implementation) | 5 | Sarika Yadav
Deployment | N/A

## Final
Product | Description | Working Hours | Responsibility
UI | A Proper PopUp Report with Types of Issues and their Severity Count | 1 | Sakshi Goyal
Service | Extract and Filter Data required data(Issue Types and Severity) about previously onboarded application from Sonar Api | 1 | Sarika Yadav
Deployment | Uploading the working Project to Cloud | 2 | Vishal M