## ProjectName
Application | # | Activity | Task | Planned Hrs | Planned Start Date | Planned End Date | Actual Hrs | Actual Start Date | Actual End Date | Resource | Status | Remarks
Airline Reservation System | 1 | Analysis | Requirement Analysis | 1 | 2019-08-06 | 2017-08-06 | 1 | 2019-08-06 | 2019-08-06 | Vishal.M, Sarika Yadav, Aman Vijay, Amit Kumar, Sakshi Goyal | Completed
|  |  | Preparing understanding document | 1 | 2019-08-06 | 2019-08-06 | 1 | 2019-08-06 | 2019-08-06 | Vishal.M | Completed
|  |  | Updating QTS | 1 | 2019-08-06 | 2019-08-06 | 0.5 | 2019-08-06 | 2019-08-06 | Sarika Yadav | Completed
|  |  | Understanding HLD/Class Diagram Prep | 2 | 2019-08-07 | 2019-08-07 | 2 | 2019-08-07 | 2019-08-07 | Sakshi Goyal | Completed
|  | Design | Unit Test Plan Preparation | 2 | 2019-08-08 | 2019-08-08 | 0.5 | 2019-08-08 | 2019-08-08 | Amit Kumar | Completed
|  |  | LLD Preparation | 3 | 2019-08-08 | 2019-08-08 | 2 | 2019-08-08 | 2019-08-08 | Vishal.M | Completed
|  |  | UTP Review | 0.5 | 2019-08-08 | 2019-08-08 | 0.5 | 2019-08-08 | 2019-08-08 | Aman Vijay | Completed
|  |  | UTP Rework | 1 | 2019-08-08 | 2019-08-08 | 0 | 2019-08-08 | 2019-08-08 | Amit Kumar | Completed
|  |  | LLD Review | 0.5 | 2019-08-08 | 2019-08-08 | 0.5 | 2019-08-08 | 2019-08-08 | Sarika Yadav | Completed
|  | Build | Coding | 15 | 2019-08-08 | 2019-08-09 | 15 | 2019-08-08 | 2019-08-10 | Aman Vijay, Amit Kumar, Sakshi Goyal, Sarika Yadav, Vishal.M | Completed
|  |  | Code Self Review | 2 | 2019-08-10 | 2019-08-10 | 2 | 2019-08-10 | 2019-08-10 | Aman Vijay, Amit Kumar, Sakshi Goyal, Sarika Yadav, Vishal.M | Completed
|  |  | Self Testing | 2 | 2019-08-10 | 2019-08-10 | 2 | 2019-08-10 | 2019-08-10 | Vishal.M, Sarika Yadav, Amit Kumar | Completed
|  |  | Rework | 4 | 2019-08-10 | 2019-08-10 | 4 | 2019-08-12 | 2019-08-13 | Aman Vijay, Amit Kumar, Sakshi Goyal, Sarika Yadav, Vishal.M | Completed
|  |  | Code Peer Review | 4 | 2019-08-10 | 2019-08-10 | 4 | 2019-08-12 | 2019-08-13 | Aman Vijay, Amit Kumar, Sakshi Goyal, Sarika Yadav, Vishal.M | Completed
|  |  | Peer Testing | 5 | 2019-08-10 | 2019-08-10 | 5 | 2019-08-12 | 2019-08-13 | Aman Vijay, Amit Kumar, Sakshi Goyal, Sarika Yadav, Vishal.M | Completed
|  |  | Test Result review | 2 | 2019-08-10 | 2019-08-10 | 2 | 2019-08-12 | 2019-08-13 | Aman Vijay, Amit Kumar, Sakshi Goyal, Sarika Yadav, Vishal.M | Completed
|  |  | Rework | 1 | 2019-08-12 | 2019-08-12 | 2 | 2019-08-13 | 2019-08-14 | Aman Vijay, Amit Kumar, Sakshi Goyal, Sarika Yadav, Vishal.M | Completed
|  |  | Code Integration | 2 | 2019-08-12 | 2019-08-12 | 2 | 2019-08-14 | 2019-08-14 | Amit Kumar | Completed
|  |  | Integration Testing | 1 | 2019-08-12 | 2019-08-12 | 1 | 2019-08-14 | 2019-08-14 | Amit Kumar | Completed
|  |  | Rework | 1 | 2019-08-13 | 2019-08-13 | 1 | 2019-08-14 | 2019-08-14 | Vishal.M, Sarika Yadav | Completed
|  |  | Test Result review | 1 | 2019-08-13 | 2019-08-13 | 1 | 2019-08-14 | 2019-08-14 | Amit Kumar, Aman Vijay | Completed
|  |  | Total Planned Hrs : | 50 |  | Total Actual Hrs: | 51